## Evidence - not LG official form
SUPPLEMENTAL WORKSHEET - NOT THE OFFICIAL LG SELF-CHECKLIST FORM
Version 1.0.1; prepared October 19, 2026. OPEN means unverified/unresolved, not N/A or passed.
ID | Area | Check | Evidence / scope | Status | Next action
PKG-01 | Packaging | App ID/version, production allowlist and official CLI package | Version 1.0.1; official @webos-tools/cli 3.2.6; metadata and build logs | PASS - automated | Upload the exact verified IPK after resolving open gates
PKG-02 | Packaging | Packaged icons, splash and launcher description | 80/130 PNG icons; 1920x1080 splash; title <=20 and description <=60 characters checked | PASS - automated | Recheck portal-specific marketing fields
PKG-03 | Packaging | Deployed source matches tested build | IPK ar/control metadata and all 12 app files match dist/ byte-for-byte | PASS - automated | Verify downloaded SHA-256 before final upload
UX-01 | Navigation | D-pad, OK, focus selection and return focus | Chromium tests; native remote not available | PASS - browser scope | Physical remote test remains open
UX-02 | Pointer | Magic Remote pointer and stationary-cursor focus handling | Chromium mouse movement and click tests, not real Magic Remote hardware | PASS - browser scope | Test pointer, wheel and D-pad switching on LG TV
UX-03 | Back | Home-level Back for selected model groups | Custom exit confirmation; general LG guide vs webOS23-25 self-checklist wording differs | OPEN | Resolve target-model interpretation in Seller Lounge and test on the selected targets
UX-04 | Privacy | Local policy screen and contact readable with remote | New browser test passes, including arrows, Back and focus restoration | PASS - browser scope | Review same screen in simulator and actual TV
UX-05 | Appearance | Mac webOS26 simulator visual launch | Church representative reports 1.0.0 looks great; no screenshot or playback result supplied | USER REPORTED | Recheck 1.0.1 after its splash/privacy update; record Mac/simulator version
CAT-01 | Catalog | Normalization and unsafe URL restrictions | Three parser tests plus browser loading/Refresh/error cases | PASS - automated | Confirm installed-app CORS and real catalog accessibility
CAT-02 | Network | Production catalog CORS | Oct 19 read-only GET with Origin:null lacks Access-Control-Allow-Origin | OPEN | Server owner to validate/configure CORS if required; no production edits authorized/performed
VID-01 | Playback | Synthetic MP4 and HLS playback, pause and Retry | Actual browser fixture playback and adapter tests; not production sermons | PASS - browser scope | Test actual sermons and native HLS on hardware
VID-02 | Playback | Actual Sunday live worship playback | Only live window confirmed: Sunday 10:30 AM U.S. Central Time | OPEN | Observe real broadcast on target LG TV, including audio and full session
VID-03 | Playback | Real archive seek/end/recovery | Native media behavior not yet exercised on LG TV | OPEN | Test MP4 ranges, seek, end, replay and failure/retry on hardware
LIFE-01 | Lifecycle | Visibility pause, cleanup, startup/stall recovery | Automated browser/adapter tests pass | PASS - automated | Validate real shell suspend/resume/standby and no background audio
TV-01 | Hardware | TV install, remote, native decoder, exit and lifecycle | No physical LG TV available; no hardware test results | OPEN | Obtain physical testing for intended model groups or ask LG about accepted validation options
CONTENT-01 | Rights | Distribution rights for sermon content | Church representative confirms rights; music is excluded for rights reasons | CHURCH CONFIRMED | Owner reviews every accessible asset and retains any required licenses/permissions
CONTENT-02 | Ratings | Actual content and age-rating questionnaire | No complete content review or portal questionnaire has been performed | OPEN | Owner reviews catalog and answers honestly; do not invent a rating
PRIV-01 | Privacy | Public and in-app policy, support contact | icbcnextsteps@gmail.com; local screen and public policy prepared | PREPARED | Owner reviews text and confirms portal accepts the URL
PRIV-02 | Privacy | No retained visitor/IP logs, advertising or analytics | No-log statement confirmed by church; no analytics/ads/account features in app | CHURCH CONFIRMED | Keep actual hosting/data practices consistent with policy
SEC-01 | Security | Credentials and unnecessary permissions | Source reviewed; no authentication secrets required; requiredACG empty; HTTPS media host restricted | SOURCE REVIEW | No independent full security audit or platform permission certification claimed
STORE-01 | Distribution | Initial territory and language | United States only confirmed; English listing prepared | CHURCH CONFIRMED | Choose United States in portal
STORE-02 | Store assets | Separate 400 icon and screen evidence | Original church cross; 1920x1080 browser JPG captures with provenance | PREPARED | Confirm current portal sizes/formats and any required simulator/device screenshot source
STORE-03 | Official forms | LG official self-checklist and UX template | Supplemental workbook/docs supplied; official binary template could not be downloaded in cloud | OPEN | Download current LG QA form; transfer only actual results; signed-in UX template may require transfer
STORE-04 | Account/submission | Authorized seller details, agreements and final upload | No Seller Lounge account accessed and no form submitted | OPEN | Church completes account declarations and explicitly submits when ready

## Read me
Purpose | Evidence transfer helper; official LG form still required
Official checklist | https://webostv.developer.lge.com/distribute/app-self-checklist
Official QA ZIP | https://webostv.developer.lge.com/assets/checklist/documents_for_app_qa.zip
Truth rule | Do not mark physical or model-specific checks passed from browser evidence